## Manual Chart
GANTT CHART GROUP 3/11 GOOGLE PLAY STORE APPS
| TASK NAME | START DATE | END DATE | DURATION (WORK DAYS) | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [6 empty] | WEEK 7 | [6 empty] | WEEK 8 | [6 empty] | WEEK 9 | [6 empty] | WEEK 10 | [6 empty] | WEEK 11 | [6 empty] | WEEK 12
[7 empty] | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun | M | T | W | Th | F | Sat | Sun
Data Mining Project
| Preprocessing | 2022-09-19 | 2022-09-21 |  |  | 0% | bar: WEEK 1 W; WEEK 4 F to WEEK 4 Sun
| Basic intial univariate descriptive statistics | 2022-09-22 | 9/25 |  |  | 0% | bar: WEEK 1 W; WEEK 4 F to WEEK 4 Sun
| Dataset description according to the main conclusions of the univariate and bivariate statistics | 2022-09-22 | 9/25 |  |  | 0% | bar: WEEK 1 Th to WEEK 2 Sun; WEEK 4 F to WEEK 4 Sun
| PCA analysis for numerical variables | 2022-10-03 | 2022-10-09 |  |  | 0% | bar: WEEK 1 Th to WEEK 2 Sun; WEEK 4 F to WEEK 4 Sun
| ACM analysis of multiple qualitative variables | 2022-10-10 | 2022-10-16 |  |  | 0% | bar: WEEK 2 M to WEEK 4 Sun
| Multiple Factorial Analysis | 2022-10-10 | 2022-10-16 |  |  | 0% | bar: WEEK 2 M to WEEK 4 Sun
| Association rules mining analysis | 2022-10-17 | 2022-10-23 |  |  | 0% | bar: WEEK 2 M to WEEK 4 Sun
| First part D3 report writing | 2022-10-17 | 2022-10-23 |  |  | 0% | bar: WEEK 4 F to WEEK 4 Sun
| Prepare for the D3 presentation | 2022-10-17 | 2022-10-23 |  |  | 0% | bar: WEEK 4 F to WEEK 4 Sun
| Task created to resolve unforeseen incidents | 2022-10-17 | 2022-10-17 |  |  | 0% | bar: WEEK 4 F to WEEK 4 Sun
| Hierarchical Clustering on original data | 2022-10-27 | 2022-11-20 |  |  | 0% | bar: WEEK 4 F to WEEK 4 Sun
| Profiling of clusters | 2022-11-17 | 2022-11-23 |  |  | 0% | bar: WEEK 4 F to WEEK 4 Sun
| Decisions tree | 2022-11-24 | 2022-11-30 |  |  | 0% | bar: WEEK 4 F to WEEK 4 Sun
| Discriminant analysis | 2022-12-01 | 2022-12-14 |  |  | 0% | bar: WEEK 4 F to WEEK 4 Sun
| Discussion and conclusions | 2022-12-01 | 2022-12-14 |  |  | 0% | bar: WEEK 4 F to WEEK 4 Sun
| Second part D3 report writing | 2022-12-01 | 2022-12-14 |  |  | 0% | bar: WEEK 4 F to WEEK 4 Sun
| Task created to resolve unforeseen incidents | 2022-12-01 | 2022-12-14 |  |  | 0% | bar: WEEK 4 F to WEEK 4 Sun
| Discussion, conclusions, comparison of results among several methods | 2022-12-15 | 2022-12-18 |  |  | 0% | bar: WEEK 4 F to WEEK 4 Sun
| Update the initial Working plan | 2022-12-18 | 2022-12-18 |  |  | 0% | bar: WEEK 4 F to WEEK 4 Sun
| Write the final report | 2022-12-01 | 2022-12-18 |  |  | 0% | bar: WEEK 4 F to WEEK 4 Sun
| Prepare for the final presentation | 2022-12-15 | 2022-12-18 |  |  | 0% | bar: WEEK 4 F to WEEK 4 Sun
| TASK NAME | START DATE | END DATE | DURATION (WORK DAYS) | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 M: WEEK 1; WEEK 2 M: WEEK 2; WEEK 3 M: WEEK 3; WEEK 4 M: WEEK 4; WEEK 5 M: WEEK 5